## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

PROJECT NUMBER	SSAD15
PROJECT NAME	LOCATION BASED ADVERTISEMENT
PROJECT MENTOR (sponsor)	VAMSEE CHAMAKURA
TEAM MEMBERS	ARUSHI SINGHAL(201516178)
	KRITIKA AGARWAL
	AAKASH MITTAL

## Status
PROJECT NUMBER	SSAD15
PROJECT NAME	LOCATED BASED ADVERTISMENT
PROJECT MENTOR (sponsor)	VAMSEE CHAMAKURA

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 1 (August 8- August 14)
Fix meeting with client	Coordination	Arushi	0.5	0.3	Done		0.2	66.6666666667
GIT Repository setup	Preparation	MENTOR	1	1.5	Done		-0.5	33.3333333333
Client meeting	Coordination	KRITIKA	5		Done
Get account and configure website	Preparation		1.5	1	Done		0.5	50
Research existing technology	Preparation	AAKASH	2	1.5	Done		0.5	33.3333333333
Project synopsis writeup	Documentation	KRITIKA	2		Done
Identify role owners	Preparation	AAKASH	20 MIN	0.6	Done
Team Meeting	Coordination	KRITIKA	45 MIN	2	Done		0.1	5
Status tracker	Documentation	Arushi	0.5		Planned
Week 2 (August 15 - August 21)
Learning Django	Preparation	KRITIKA and ARUSHI			Done
Algorithmic research	Preparation	AAKASH			Done

Project synopsis writeup	Documentation	KRITIKA	1		Done

Team Meeting	Coordination	AAKASH	30 min		Done
Status tracker	Documentation	Arushi	1		Done
Meeting Minutes	Documentation	AAKASH			Done

Week 3 (August 22 – August 28)
Mom of meeting (6th september)	Documentation	AAKASH	30 min		Done	Deadline 6th September
Project Plan detailed proposal	Documentation	AAKASH	2hr		Done	Deadline 8th September
Use Case description	Documentation	KRITIKA and ARUSHI	3hrs		Done	Deadline 10th September
Managing & Planning Team Acitivities	Coordination	KRITIKA			Done

Week 4(August 29-Sep4)

Week 5(September5-September11)

Week 6(September11-17)

Week 7(September18-24)
complete “get user location”	Development	Aakash