## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

PROJECT NUMBER	SSAD15
PROJECT NAME	LOCATION BASED ADVERTISEMENT
PROJECT MENTOR (sponsor)	VAMSEE CHAMAKURA
TEAM MEMBERS	ARUSHI SINGHAL(201516178)
	KRITIKA AGARWAL
	AAKASH MITTAL

## Status
PROJECT NUMBER	SSAD15
PROJECT NAME	LOCATED BASED ADVERTISMENT
PROJECT MENTOR (sponsor)	VAMSEE CHAMAKURA

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 1 (August 22- August 28)
Fix meeting with client	Coordination	Kritika	0.5	0.6	Ongoing	client is busy this week	-0.1	16.6666666667
Meeting Minutes	Preparation	Kritika and Aakash	0.5	1	Ongoing		-0.5	50
Client meeting	Coordination	KRITIKA			Delayed	client is out for a week
Mailing TA	Preparation	Arushi	0.4	0.5	Done		-0.1	20
Research existing technology	Preparation	AAKASH	1	1.5	Ongoing		-0.5	33.3333333333
Project synopsis writeup	Documentation	AAKASH	0.5	0.5	Done		0	0
Identify role owners	Preparation	AAKASH	20 MIN	0.6	Done
Team Meeting	Coordination	KRITIKA	1	1.5	Done		0.1	6.6666666667
Status tracker	Documentation	Arushi	0.5	0.6	Done		-0.1	16.6666666667

Week 3 (August 22 - sept 28)

Week 4

Week 5

Week 6